## Slide 1
MEMORANDUM
To:
All staff and department heads
From:
Management · Human Resources
Date:
October 2026
Re:
Trial of a 32-hour, four-day week at full pay
A four-day week from
January 2027
Six months from January 4, at full pay
Exhibit 1 · A quiet Friday morning (illustrative)
Decided
2026 · 10
Notes: This memo records a management decision: from Monday, January 4, 2027, the whole company will trial a four-day, 32-hour week at full pay for six months, after two months of preparation in November and December. The pages that follow set out the terms, the reasons, the evidence for and against, how each department will run it, how we will judge it, when we will stop, and who does what. Outside figures come from published research and official sources, named on each page.

## Slide 2
MEMORANDUM
Four-day week pilot · Decision
Management · Human Resources
Page
2
of 16
Decision
32 hours, full pay, six months
1.
Hours and pay
All full-time staff work 32 hours a week. Pay, bonus base, leave and
benefits stay the same
2.
Dates
Prepare in November and December. Trial from January 4 to June
30, 2027
3.
Model
Each department picks one of three models. Support and always-on
roles stagger
4.
Keep or stop
We decide in July on measures agreed now. A team that trips a stop
rule goes back at once
Notes: Four terms. First, every full-time employee, management included, works 32 hours a week instead of 40, with salary, bonus base, leave and benefits unchanged. Second, November and December are for preparation, the trial starts on Monday, January 4, 2027 and ends on June 30. Third, departments choose their model from three options on a later page, and customer support and other always-on roles can only use staggered days off. Fourth, this is a trial, not a promise: in July we decide, against measures agreed in advance, whether to keep it, and any team that trips a stop rule during the trial returns to five days straight away.

## Slide 3
MEMORANDUM
Four-day week pilot · Decision
Management · Human Resources
Page
3
of 16
Reasons
Burnout, retention, hiring. Not revenue
Less burnout
82%
of 28 UK organisations revisited a year on saw
better staff wellbeing
Keeping people
50%
of them saw less turnover. 15% of staff would not
go back to five days for any raise
Hiring
32%
of them hired more easily. One council saw job
applications rise by more than 120%
Exhibit 2 · A weekday morning (illustrative)
Revenue, accurately: "broadly the same"
Source: Autonomy et al., UK pilot reports, Feb 2023 and Feb 2024, self-reported. University of Salford, Jul 2025. Images are AI-generated
Notes: Why we are doing this. First, burnout: a year after the UK pilot, researchers went back to 28 organisations and 82% reported better staff wellbeing. Second, retention: half of them reported lower turnover, and at the end of the trial 15% of employees said no pay rise would get them back to a five-day week. Third, hiring: 32% reported easier recruitment, and South Cambridgeshire Council saw job applications rise by more than 120% after its switch. These figures are self-reported by organisations and staff, and the UK pilot was run with an advocacy group, so they show a direction, not a forecast for us. Revenue growth is not one of our reasons, and a later page explains why.

## Slide 4
MEMORANDUM
Four-day week pilot · Decision
Management · Human Resources
Page
4
of 16
Evidence
Burnout fell in trial firms. Not in controls.
Burnout (lower is better, 1
to 5)
Before
After
2.90
2.94
2.83
2.38
Mental health (1 to 5)
Before
After
2.90
2.93
2.93
3.32
Physical health (1 to 5)
Before
After
3.06
3.09
3.01
3.29
Trial: 141 orgs, 2,896 staff
Control: 12 firms, 285 staff
Authors' caveat
“our findings probably
overestimate the true effect”
Not randomised, firms
volunteered, staff reported.
Trust the direction, not
the size.
Source: Fan et al., Nature Human Behaviour, Jul 2025. Published online 2025-07-21
Notes: This is the largest peer-reviewed study so far: 141 organisations and 2,896 employees in six countries, compared with 12 US companies and 285 people that did not change their hours. In the trial firms, weekly hours fell from 39.21 to 34.01, burnout fell from 2.83 to 2.38, mental health rose from 2.93 to 3.32 and physical health from 3.01 to 3.29. The control group barely moved: burnout 2.90 to 2.94, mental health 2.90 to 2.93, physical health 3.06 to 3.09. The chart shows the change. This is the main reason we are running a trial. The limits matter too: the study was not randomised, the firms chose to take part and were likely more open to flexible work, every result is self-reported, and the authors themselves say their findings probably overestimate the true effect of a four-day week. The paper did not measure company productivity.

## Slide 5
MEMORANDUM
Four-day week pilot · Decision
Management · Human Resources
Page
5
of 16
Costs
71% felt less burned out. 62% said work sped up
← Better
No change
Worse →
Burnout
71%
7%
22%
Work stress
39%
48%
13%
Sleep problems
40%
45%
15%
Workload
2%
78%
20%
Pace of work
2%
36%
62%
Hours actually
worked
38→34
hrs
Four hours less a
week, not eight
Source: Autonomy et al., UK pilot report, Feb 2023, self-reported. "Better" includes a slower pace and a lighter workload
Notes: Staff in the 61 UK pilot companies felt both sides. 71% reported less burnout, 39% less stress and 40% fewer sleep problems. But 62% said the pace of work rose, only 2% said it slowed, and 20% said their workload grew. Hours also fell by less than a full day: self-reported weekly hours went from 38 to 34. Brazil saw the same pattern, with 48.2% of staff feeling a faster pace and a third of the companies hiring to cope. That is why we cut meetings and process first rather than squeezing five days of work into four.

## Slide 6
MEMORANDUM
Four-day week pilot · Decision
Management · Human Resources
Page
6
of 16
Revenue
Revenue held broadly steady. It did not jump
Companies' revenue, for instance, stayed
broadly the same over the trial period,
rising by 1.4% on average.
Autonomy et al., UK pilot report, February 2023
Meaning
revenue held level, up 1.4% weighted by firm size
One report, two measures
Never mix them, and name both when
you quote one
+1.4%
23 firms, start to end of the trial
+34.5%
Another 24 firms, against the
year before
Notes: You may have read that a four-day week raised revenue by 35%. That misreads the UK report. It gives two numbers. For the 23 companies that reported it, revenue from the start to the end of the trial rose 1.4% on average, weighted by company size, which the report itself calls broadly the same. The 35% compares a different group of 24 companies with the same period a year earlier, so it includes ordinary business growth and is not the same comparison. Other pilots tell the same story: in Germany revenue and profit showed no significant change from the year before, and in Brazil 27.3% of companies saw revenue fall and 36.4% saw profit fall. Microsoft Japan's often-quoted 39.9% rise in sales per employee covers one month, August 2019, and Microsoft later added that it was not achieved by the four-day week alone. Our expectation for revenue is to hold it, not to grow it.

## Slide 7
MEMORANDUM
Four-day week pilot · Decision
Management · Human Resources
Page
7
of 16
Staying power
Advocates report 90% kept it, others fewer
Pilot
When
Still running
Sample
Source
UK
End of pilot
92%
61 firms
Advocate
Academics with advocates
UK
A year on
at least 89%
61 firms
Advocate
Same
Global sample
12–24 months
90%
197 firms
Advocate
Unreviewed working paper
Germany
End of pilot
73%
41 orgs
Independent
University with advocates
Germany
Two years on
70%
40 orgs
Independent
University follow-up
Portugal
End of pilot
17, 5 scaled back
21 firms
Independent
Government, university
Brazil
A year on
10% (2 firms)
20 firms
Press
Press report
Source: Autonomy et al. 2023, 2024. Schor et al. 2025. University of Münster 2024, 2026. Gomes et al. 2024. InfoMoney 2025
Notes: How many kept going depends on who counted and for how long. In the UK, 56 of 61 companies continued at the end of the trial and at least 54 were still running it a year later. Across 197 companies tracked by the advocacy group 4 Day Week Global, about one in ten went back to five days. These companies volunteered and were recruited by an advocacy group, so they wanted it to work. Outside that circle, and over longer periods, the numbers are much lower. In Germany, 30% of 40 organisations had stopped two years on, most often because they could not deliver reliably at peak times or found the model too rigid. In Portugal, 4 of 21 firms went back to five days and 5 scaled back. In Brazil, only 2 of 20 companies formally kept it a year later.

## Slide 8
MEMORANDUM
Four-day week pilot · Decision
Management · Human Resources
Page
8
of 16
Weighing
Evidence backs a bounded trial. Not a windfall.
What holds up
Burnout down, health up
141 organisations, controlled but not randomised
Most firms kept going
UK: at least 89% still running a year on
Process changes help
Portugal: 8% went back after two or more changes
What to watch
No revenue boost
UK +1.4%, Germany flat, 27.3% of Brazil's firms down
Faster pace
UK: 62% said work sped up. Brazil: a third of firms hired
Support roles struggle
Krystal's staggered support desk went back
Drop-outs over time
Germany: 30% stopped in two years. Brazil: 2 of 20 kept it
So we trial it, with limits, measures and stop rules set first
Source: Fan et al. 2025. Autonomy et al. 2023, 2024. Gomes et al. 2024. Münster 2026. Brazil pilot 2024. InfoMoney 2025. Krystal 2023
Notes: Put the two sides together. What holds up: staff health really did improve, most firms that finished chose to continue, and firms that changed how they work were more likely to stick with it. What to watch: revenue did not rise because of it, the pressure moved from hours to intensity, customer support and always-on roles are the hardest, and some firms drop out over time. The evidence supports a trial with limits, measures and the means to stop. It does not support the claim that one day less brings more revenue. That is how we will run it.

## Slide 9
MEMORANDUM
Four-day week pilot · Decision
Management · Human Resources
Page
9
of 16
Models
Three models by team. Always-on roles stagger
Exhibit 3 · Fridays off (illustrative)
Exhibit 4 · Staggered (illustrative)
Exhibit 5 · Fortnightly (illustrative)
Fridays off
How
The whole team off on Friday
Suits
Close teams, few outside calls
Seen in
32% of UK pilot firms
Staggered
For support
How
Each person takes one weekday off
Suits
Support and ops, five-day cover
Seen in
25% of UK pilot firms
9-day fortnight
How
One day off a fortnight, about 7.1 hours on
the other nine
Suits
Teams that cannot leave a whole day
Seen in
Over 60% of Portugal's staff
Source: Autonomy et al., UK pilot report, Feb 2023. Gomes et al., Jul 2024. One model per team: mixed schedules were one reason Magyar Telekom ended its trial. Images
are AI-generated
Notes: Department heads choose the model. Fridays off: the whole department is off on Friday, which suits teams that work closely together and deal little with outsiders, with one named contact on call. Staggered: each person takes a different weekday off so all five days are covered, the only option for customer support and operations. Nine days in two weeks: one day off every second week and about 7.1 hours on each of the other nine days, 64 hours over the fortnight, for delivery teams that cannot step away for a whole day. Among 44 UK pilot companies that answered, 32% gave everyone Friday off and 25% had no shared day off. In Portugal more than 60% of staff took a day off every two weeks, though that trial cut hours to 36, not 32. One model per team: Magyar Telekom found that running four-day and five-day schedules side by side made coordination hard, one of the reasons it ended its trial after 18 months.

## Slide 10
MEMORANDUM
Four-day week pilot · Decision
Management · Human Resources
Page
10
of 16
Coverage
The floor: 80% of staff on duty every weekday
Example: a ten-person support team, staggered
Mon
Tue
Wed
Thu
Fri
Agent A
Off
Agent B
Off
Agent C
Off
Agent D
Off
Agent E
Off
Agent F
Off
Agent G
Off
Agent H
Off
Agent I
Off
Agent J
Off
On duty
8 / 10
8 / 10
8 / 10
8 / 10
8 / 10
Exhibit 6 · The support desk (illustrative)
On duty, busiest day
Krystal
50%
3-day first replies
SOSE, Scotland
94% → 92%
Services held or better
South Cambridgeshire
21 / 24
Source: Krystal, Sep 2023, company account. Civil Service World, Aug 2025. University of Salford, Jul 2025. Image is AI-generated
Notes: Staggering is where things go wrong. Krystal, a UK hosting company, gave half its support team Mondays off and half Fridays off, so on the busiest day only half the team was in. Support slowed, staff felt more pressure, and the six-month trial ended early: from October 2023 the team went back to five days with an earlier finish and five more hires. Scotland's SOSE kept its service going with staggered days, but the share of enquiries answered within three working days slipped from 94% to 92%, while the number answered on time went up. South Cambridgeshire Council reported 21 of 24 services improved or held steady, though its evaluators did not prove the four-day week caused it. Our rule: support and always-on teams spread days off evenly from Monday to Friday, so at least 80% of the team is on duty every weekday, and everyone has a cover buddy. If a day falls below 80%, the department head fixes it that day.

## Slide 11
MEMORANDUM
Four-day week pilot · Decision
Management · Human Resources
Page
11
of 16
Arithmetic
25% more output per hour
Weekly hours
40 → 32
Total output
the same
Output per hour
40 ÷ 32 = 1.25
Rise needed
25%
A warning
Krystal went back to five days
partly because the extra rest did not
lift output by the 20% it needed.
So we cannot just ask people to push
harder. Meetings and process
go first.
Source: Krystal, Sep 2023, company account
Notes: This is the plain arithmetic behind the whole decision. We work 40 hours a week today. Cut to 32 with the same total output, and every hour has to produce 25% more. Better rest alone will not close a gap that size. Krystal's support team is the example: the company said the extra recovery time did not raise output by the 20% it needed, the work became more stressful, and it went back to five days. So the process changes on the next page are not a nice extra. They decide whether the trial can work at all.

## Slide 12
MEMORANDUM
Four-day week pilot · Decision
Management · Human Resources
Page
12
of 16
Process
Fix process first: 8% of those firms reverted
1
30-minute meetings
No meetings on Wednesday mornings. Over an hour
needs sign-off
2
Written updates
One weekly note replaces the status meeting
3
Two sign-offs at most
For routine approvals
4
A stop-doing list per team
The reports and steps we drop for the trial
Exhibit 7 · A whiteboard stand-up (illustrative)
Portugal, 21 firms: share that went back
8%
Two or more changes
38%
One change or none
Source: Gomes and Fontinha, Portugal pilot final report, Jul 2024, 21 firms. Image is AI-generated
Notes: If each hour must produce 25% more, the hours that produce nothing have to go first. In Portugal's government-backed pilot, only 8% of the firms that made two or more process changes went back to five days, against 38% of those that made one change or none. We are making four changes. Meetings default to 30 minutes, Wednesday mornings are meeting-free, and anything over an hour needs the department head's approval. Weekly status meetings become one written update. Routine approvals need no more than two signatures. Most important, every department files a stop-doing list by November 30, naming the reports and steps it will drop during the trial.

## Slide 13
MEMORANDUM
Four-day week pilot · Decision
Management · Human Resources
Page
13
of 16
Schedule
Start January 4. Decide by July 31.
Oct
2026
Nov
Dec
Jan
2027
Feb
Mar
Apr
May
Jun
Jul
Prepare, 2 months
Trial, 6 months · 32 hours a week
Decide
Oct 2026
This memo
Teams pick a model
Nov 30
Plans due
Rota, stop-doing list, on-call cover
Jan 4, 2027
Trial starts
32 hours a week, same pay
Mar 31
Midpoint review
Second survey, rotas can change
Jun 30
Trial ends
Third survey
By Jul 31
Decision
Team by team, against the baseline
Source: Autonomy et al., UK pilot report, Feb 2023, for two months of preparation before a six-month trial. The baseline is November and December
Notes: The timeline. This memo goes out in October. Preparation starts on November 1: HR runs the first staff survey, and each department pulls its November and December figures for customer response, output, overtime and contractor spend as the baseline. Rotas, stop-doing lists and cover plans are due by November 30. The trial starts on Monday, January 4, 2027. On March 31 we review it at the midpoint with a second survey, and rotas can change. It ends on June 30 with a third survey. By July 31 we decide, department by department, against the baseline. In weeks with a public holiday, the holiday is the short day and there is no extra day off.

## Slide 14
MEMORANDUM
Four-day week pilot · Decision
Management · Human Resources
Page
14
of 16
Stop rules
One breach, back to five days
Customers
first response time
IF
over 10% slower than baseline for 4 weeks running
Output
the team's core measure
IF
over 5% below baseline for 2 months running
Cost
overtime and contractors
IF
added cover costs over 3% of the team's payroll
People
burnout and stress
IF
the midpoint survey scores worse than baseline
Then: five days again within two weeks. HR takes it to management, pay is unchanged and other teams
carry on
Source: Autonomy et al., UK pilot report, Feb 2023, on a conditional four-day week. The thresholds are our policy, not research findings
Notes: We judge the trial and stop it with the same four measures: customers, output, cost and people, each against the November and December baseline. Any breach is acted on straight away, not in July. Customers: first response time more than 10% slower than baseline for four weeks running. Output: the department's own core measure, such as sales, on-time delivery or tickets closed, more than 5% below baseline for two months running. Cost: overtime and contractor spend added to cover the day off exceeds 3% of the department's payroll, a sign the work has moved rather than shrunk. People: burnout or stress in the midpoint survey worse than at baseline. When a rule trips, HR takes it to management within two weeks and that department returns to five days while the others carry on. Going back to five days does not affect pay.

## Slide 15
MEMORANDUM
Four-day week pilot · Decision
Management · Human Resources
Page
15
of 16
Roles
Rotas and stop-doing lists are due November 30
Who
Preparation (Nov to Dec)
Trial (Jan to Jun)
Management
Approve plans, confirm stop rules
Review monthly, rule on any breach
Human Resources
Baseline survey, attendance and rota rules
Midpoint and final surveys, evaluation
Department heads
Model, rota, stop-doing list by Nov 30
Weekly customer and output measures,
monthly report
Support teams
Stagger days off, pair everyone with a
cover buddy
At least 80% on duty every weekday
All staff
Baseline survey, ideas on what to cut
Days off stay off, urgent work goes on-call
Source: Autonomy et al., UK pilot report, Feb 2023, for the cover buddies of staggered teams
Notes: Who does what. Management approves each department's plan and confirms the stop-rule thresholds, then reviews the measures every month during the trial and decides when a rule trips. HR runs the three surveys, sets the time-keeping and rota rules, answers questions and writes the final evaluation. Department heads carry the most weight: pick the model, set the rota, file the stop-doing list by November 30, then track customer and output measures every week and report monthly. Support and always-on teams stagger their days off and pair everyone with a cover buddy so at least 80% of the team is in every weekday. Everyone else: please take the baseline survey and tell your department head which meetings and steps you would cut. Days off stay off, and anything urgent goes to the on-call rota.

## Slide 16
MEMORANDUM
Decision
Trial 32 hours at full pay, stop on any breach
1.
From January 4, 2027: 32 hours a week, same pay
2.
Any stop rule halts it. We decide in July
Signed:
Management
October 2026
Drafted:
Human Resources
Copies:
All staff, all department heads
Decided
2026 · 10
Notes: The two decisions once more. First, from January 4, 2027, the whole company trials a four-day, 32-hour week at full pay for six months. Second, any department that trips a stop rule goes back to five days, and by the end of July we decide on the measures whether to keep it. This memo is issued by management, drafted by Human Resources and copied to all staff and department heads. Questions go to your department head or to HR.